## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 16 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY |  | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
| Responsibility | [5 empty] | February |  |  |  | March |  |  |  | April |  |  |  | May
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Research | J + B | 1 | 12 | 1 | 12 | 100%
Concepts/mechanisms | J + B | 2 | 12 | 2 | 12 | 100%
Design (main body) | J | 2 | 12 | 2 | 12 | 100%
Design (wheelbase) | B | 2 | 12 | 2 | 12 | 100%
Simulation (fusion) | J | 6 | 8 | 6 | 8 | 100%
Simulation (CoppeliaSim) | B | 5 | 9 | 5 | 9 | 100%
Evaluation (Proposal) | J + B | 4 | 2 | 4 | 2 | 100%
Evaluation (PDR) | J + B | 7 | 4 | 7 | 4 | 100%
Evaluation (CDR) | J + B | 12 | 2 | 12 | 2 | 100%
Project proposal | J + B | 3 | 1 | 3 | 1 | 100%
PDR | J + B | 6 | 1 | 6 | 1 | 100%
CDR | J + B | 11 | 1 | 11 | 1 | 100%
Final presentation | J + B | 14 | 1 | 14 | 1 | 100%